## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
T001 | Project Kickoff Meeting | John Doe | 2024-03-15 | 2024-03-15 | 1 | High | Completed
T002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | 10 | High | In Progress | T001
T003 | Design Phase | Mike Chen | 2024-03-26 | 2024-04-10 | 15 | Medium | Planned | T002
T004 | Development Phase | Lisa Wong | 2024-04-11 | 2024-05-15 | 35 | High | Not Started | T003
T005 | Testing & Quality Assurance | Tom Harris | 2024-05-16 | 2024-06-10 | 35 | High | Not Started | T004
T006 | Deployment & Go-Live | Emma Clark | 2024-06-11 | 2024-06-15 | 5 | Medium | Not Started | T005