## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
TSQ-001 | Quarterly Project Kickoff | John Doe | 2024-03-01 | 2024-03-05 | 5 | High | Completed | None | Finalize scope and team assignments.
TSQ-002 | Market Research Phase | Sarah Lee | 2024-03-06 | 2024-03-25 | 20 | Medium | In Progress | TSQ-001 | Collect customer insights and competitor data.
TSQ-003 | Product Design Development | Mike Chen | 2024-03-26 | 2024-04-15 | 21 | High | Planned | TSQ-002 | Finalize wireframes and UI mockups.
TSQ-004 | Development Sprint 1 | Lena Patel | 2024-04-16 | 2024-05-15 | 30 | High | Not Started | TSQ-003 | Build core functionality.
TSQ-005 | QA & Testing Phase | David Kim | 2024-05-16 | 2024-06-15 | 30 | Medium | Not Started | TSQ-004 | Conduct unit and user testing.
TSQ-006 | Deployment & Launch | Emma Wilson | 2024-06-16 | 2024-06-30 | 15 | High | Not Started | TSQ-005 | Deploy to production and launch campaign.