## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Priority | Status
Project Kickoff Meeting | Sarah Johnson | 2024-03-01 | 2024-03-01 | 1 | High | Completed
Market Research | Mark Thompson | 2024-03-04 | 2024-03-15 | 13 | Medium | In Progress
Design Brand Identity | Linda Chen | 2024-03-18 | 2024-04-05 | 19 | High | Not Started
Develop Website Prototype | David Park | 2024-04-06 | 2024-04-20 | 15 | Medium | Planned
Client Review & Feedback | Sarah Johnson | 2024-04-23 | 2024-04-25 | 3 | High | Scheduled
Finalize Content & Copy | Emily Davis | 2024-04-30 | 2024-05-10 | 11 | Medium | Not Started
Launch Website | Mark Thompson | 2024-05-15 | 2024-05-15 | 1 | High | Planned
Post-Launch Evaluation | Linda Chen | 2024-06-01 | 2024-06-05 | 5 | Low | Planned