## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
T-001 | Product Vision Finalization | Alex Chen | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | None
T-002 | Market Research & Analysis | Sara Kim | 2024-03-05 | 2024-03-20 | 16 | Medium | Planned | T-001
T-003 | UI/UX Design Sprint | Jordan Lee | 2024-03-21 | 2024-04-05 | 15 | High | Not Started | T-002
T-004 | Backend Development Phase | Miguel Torres | 2024-04-06 | 2024-05-30 | 55 | Critical | Not Started | T-003
T-005 | QA Testing & Bug Resolution | Nina Patel | 2024-06-01 | 2024-06-30 | 30 | High | Not Started | T-004