## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies
T001 | Project Initiation | John Smith | 2024-03-01 | 2024-03-05 | 5 | Completed | High | None
T002 | Requirements Gathering | Anna Lee | 2024-03-06 | 2024-03-15 | 10 | In Progress | High | T001
T003 | Design Phase | Mike Chen | 2024-03-16 | 2024-03-25 | 10 | Not Started | Medium | T002
T004 | Development | Lisa Wong | 2024-03-26 | 2024-04-15 | 20 | Not Started | High | T003
T005 | Testing & QA | Robert Kim | 2024-04-16 | 2024-04-30 | 15 | Not Started | High | T004
T006 | Deployment | Sarah Patel | 2024-05-01 | 2024-05-03 | 3 | Not Started | Medium | T005