## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | Sarah Chen | 2024-03-15 | 2024-03-15 | 1 | High | Completed |  | Finalize project goals and team roles.
T002 | Requirements Gathering | James Reed | 2024-03-16 | 2024-03-25 | 10 | High | In Progress | T001 | Collect stakeholder needs and document functional requirements.
T003 | Design Phase | Lisa Wong | 2024-03-26 | 2024-04-10 | 15 | Medium | Planned | T002 | Develop UI/UX mockups and system architecture.
T004 | Development | Team A | 2024-04-11 | 2024-05-15 | 35 | High | Planned | T003 | Build core application features based on design.
T005 | Testing & QA | Mike Tran | 2024-05-16 | 2024-05-31 | 16 | High | Planned | T004 | Conduct unit, integration, and user acceptance testing.
T006 | Go-Live & Deployment | Admin Team | 2024-06-01 | 2024-06-03 | 3 | Critical | Planned | T005 | Deploy to production environment and monitor performance.