## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
T001 | Project Initiation | John Doe | 2024-03-01 | 2024-03-05 | 5 | High | In Progress | -
T002 | Requirements Gathering | Jane Smith | 2024-03-06 | 2024-03-15 | 10 | High | Planned | T001
T003 | Design Phase | Mike Johnson | 2024-03-16 | 2024-03-31 | 16 | Medium | Not Started | T002
T004 | Development Phase | Sarah Lee | 2024-04-01 | 2024-05-15 | 60 | High | Planned | T003
T005 | Testing & QA | David Brown | 2024-05-16 | 2024-06-10 | 35 | High | Not Started | T004
T006 | Deployment | Lisa Wong | 2024-06-11 | 2024-06-15 | 5 | Medium | Planned | T005