## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Duration (Days) | Progress (%) | Dependencies | Priority
T-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | Completed | 1 | 100% |  | High
T-002 | Requirement Gathering | John Smith | 2024-04-02 | 2024-04-15 | In Progress | 14 | 65% | T-001 | High
T-003 | Design Phase Final Review | Lisa Wong | 2024-04-16 | 2024-04-25 | Planned | 10 | 0% | T-002 | Medium
T-004 | Development Start | Mike Johnson | 2024-04-26 | 2024-05-31 | Not Started | 36 | 0% | T-003 | High
T-005 | Testing & QA Cycle | Sarah Lee | 2024-06-01 | 2024-06-30 | On Hold | 30 | 15% | T-004 | Critical