## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation | Progress (%)
T-001 | Project Initiation | John Smith | 2024-03-01 | 2024-03-15 | 15 | High | Completed | None | Project Manager, PMO Team | 100%
T-002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-04-10 | 35 | Medium | In Progress | T-001 | Business Analysts, Stakeholders | 65%
T-003 | Design Phase | Michael Chen | 2024-04-11 | 2024-05-15 | 35 | High | Planned | T-002 | UI/UX Team, Design Leads | 0%
T-004 | Development | David Kim | 2024-05-16 | 2024-07-31 | 86 | High | Not Started | T-003 | Software Engineers, DevOps Team | 0%
T-005 | Testing & QA | Lisa Wong | 2024-08-01 | 2024-08-31 | 31 | High | Planned | T-004 | QA Team, Test Managers | 0%
T-006 | Deployment | Robert Garcia | 2024-09-01 | 2024-09-15 | 15 | Critical | Not Started | T-005 | Operations Team, Cloud Admins | 0%