## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
TSK-001 | Project Kickoff Meeting | John Smith | 2024-01-15 | 2024-01-15 | 1 | High | Completed |  | Initial planning and team alignment.
TSK-002 | Requirements Gathering | Sarah Lee | 2024-01-16 | 2024-02-15 | 30 | High | In Progress | TSK-001 | Collect stakeholder input and finalize scope.
TSK-003 | Design Phase | Mike Chen | 2024-02-16 | 2024-03-31 | 46 | Medium | Planned | TSK-002 | Wireframes and UI mockups.
TSK-004 | Development Phase | Alex Rivera | 2024-04-01 | 2024-06-30 | 90 | High | Planned | TSK-003 | Backend and frontend implementation.
TSK-005 | Testing & QA | Lisa Wong | 2024-07-01 | 2024-07-31 | 31 | High | Planned | TSK-004 | Functional and performance testing.
TSK-006 | Deployment | David Kim | 2024-08-01 | 2024-08-05 | 5 | High | Planned | TSK-005 | Live deployment to production.
TSK-007 | Post-Deployment Review | Team Lead | 2024-08-10 | 2024-08-10 | 1 | Medium | Planned |  | Gather feedback and document lessons learned.