## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status
T001 | Project Initiation | John Doe | 2024-03-15 | 2024-03-18 | 4 | High | Completed
T002 | Requirements Gathering | Jane Smith | 2024-03-19 | 2024-03-25 | 7 | Medium | In Progress
T003 | Design Phase | Mike Johnson | 2024-03-26 | 2024-04-05 | 10 | High | Planned
T004 | Development | Sarah Lee | 2024-04-06 | 2024-05-10 | 35 | High | Not Started
T005 | Testing & QA | David Brown | 2024-05-11 | 2024-05-25 | 15 | Medium | Planned