## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T-001 | Project Initiation Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | 1 | High | Planned |  | Finalize project scope and objectives.
T-002 | Market Research | Mike Johnson | 2024-03-16 | 2024-03-25 | 9 | Medium | In Progress | T-001 | Collect customer feedback and analyze trends.
T-003 | Design Phase Finalization | Sarah Lee | 2024-03-26 | 2024-04-10 | 15 | High | Not Started | T-002, T-004 | Finalize UI/UX designs based on research.
T-004 | Develop MVP Prototype | David Brown | 2024-04-11 | 2024-05-15 | 35 | High | Not Started | T-003 | Build a working prototype for early testing.
T-005 | Stakeholder Review & Feedback | Clara White | 2024-05-16 | 2024-05-18 | 3 | Medium | Planned | T-004 | Review prototype and collect stakeholder input.