## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | High | -
T002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | In Progress | High | T001
T003 | Design Phase Final Review | Mike Johnson | 2024-04-01 | 2024-04-10 | Planned | Medium | T002
T004 | Development Sprint 1 | Emily Davis | 2024-04-11 | 2024-04-25 | High Priority | High | T003
T005 | Testing & Quality Assurance | David Brown | 2024-05-01 | 2024-05-15 | Pending Start | Medium | T004