## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status
T001 | Project Planning | John Smith | 2024-03-01 | 2024-03-15 | 15 | High | In Progress
T002 | Design Phase | Anna Lee | 2024-03-16 | 2024-04-10 | 25 | Medium | Not Started
T003 | Development Phase | Marcus Tan | 2024-04-11 | 2024-06-30 | 91 | High | Planned
T004 | Testing & QA | Sarah Kim | 2024-07-01 | 2024-07-31 | 31 | Medium | Scheduled
T005 | Deployment & Review | David Reed | 2024-08-01 | 2024-08-15 | 15 | Low | Not Started