## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Duration (Days) | Dependencies | Progress (%)
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | Completed | Low | 1 | None | 100
T002 | Requirements Gathering | Jane Doe | 2024-04-02 | 2024-04-15 | In Progress | Medium | 14 | T001 | 65
T003 | UI/UX Design Phase | Alex Chen | 2024-04-16 | 2024-05-10 | Planned | High | 35 | T002 | 0
T004 | Backend Development | Mike Brown | 2024-05-11 | 2024-07-30 | Scheduled | High | 90 | T003 | 0
T005 | Testing & QA Phase | Sarah Lee | 2024-08-01 | 2024-08-31 | Not Started | Medium | 31 | T004 | 0