## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Initiation & Planning | John Doe | 2024-04-01 | 2024-04-15 | 15 | High | In Progress | None | Finalize project scope and objectives.
T002 | Requirements Gathering | Jane Smith | 2024-04-16 | 2024-05-05 | 21 | High | Not Started | T001 | Collect user and technical requirements.
T003 | Design Phase | Mike Johnson | 2024-05-06 | 2024-06-10 | 35 | Medium | Not Started | T002 | Create wireframes and UI mockups.
T004 | Development | Sarah Lee | 2024-06-11 | 2024-08-30 | 71 | High | Not Started | T003 | Implement core features and modules.
T005 | Testing & QA | David Brown | 2024-09-01 | 2024-10-15 | 45 | High | Not Started | T004 | Conduct unit, integration, and user testing.
T006 | Deployment | Lisa Wong | 2024-10-16 | 2024-10-30 | 25 | Critical | Not Started | T005 | Deploy to production environment.