## Worksheet
Task ID | Task Name | Description | Assignee | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Progress (%) | Notes
T-001 | Project Initiation Meeting | Conduct kickoff meeting to align project goals and stakeholders. | Alice Johnson | 2024-04-01 | 2024-04-03 | 3 | High | Completed | - | 100% | No follow-up required.
T-002 | Requirements Gathering | Collect and document functional and non-functional requirements from stakeholders. | Bob Smith | 2024-04-04 | 2024-04-15 | 13 | High | In Progress | T-001 | 65% | Review with legal team pending.
T-003 | Design Phase | Develop UI/UX and system architecture designs. | Carol Lee | 2024-04-16 | 2024-05-10 | 26 | Medium | Not Started | T-002 | 0% | Design review scheduled for May 5.
T-004 | Development Phase | Implement features based on approved designs. | David Park | 2024-05-11 | 2024-07-30 | 81 | High | Not Started | T-003 | 0% | Team to be assigned after design approval.
T-005 | Testing & QA | Conduct unit, integration, and user acceptance testing. | Eve Thompson | 2024-08-01 | 2024-08-31 | 31 | High | Not Started | T-004 | 0% | Final bug fixes to be completed before release.
T-006 | Deployment | Deploy application to production environment. | Frank Reed | 2024-09-01 | 2024-09-05 | 5 | Critical | Not Started | T-005 | 0% | Post-deployment support to begin immediately.