## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (days) | Priority | Status | Dependencies | Resource Required
T001 | Project Initiation | John Smith | 2024-03-01 | 2024-03-05 | 5 | High | In Progress |  | Project Manager, Stakeholders
T002 | Market Research | Sarah Lee | 2024-03-06 | 2024-03-15 | 10 | Medium | Planned | T001 | Research Team, Data Analysts
T003 | Design Phase | Michael Chen | 2024-03-16 | 2024-04-10 | 35 | High | Not Started | T002 | UI/UX Designers, Creative Lead
T004 | Development Phase | Emma Rodriguez | 2024-04-11 | 2024-06-30 | 90 | Critical | Not Started | T003, T005 | Software Engineers, QA Team
T005 | System Testing | Liam Kim | 2024-07-01 | 2024-07-15 | 15 | High | Planned | T004 | QA Engineers, Test Managers
T006 | Deployment & Go-Live | Nina Patel | 2024-07-16 | 2024-07-25 | 10 | High | Not Started | T005 | Operations Team, IT Admins