## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Budget Allocation ($) | Status | Progress (%) | Priority
TSK-001 | Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | 5,000 | Completed | 100 | High
TSK-002 | Market Research & Analysis2024-03-02 | 2024-03-15 | 14 | Marketing Lead | 15,000 | In Progress | 75 | High
TSK-003 | Product Design Finalization | 2024-03-16 | 2024-04-10 | 35 | Design Team Lead | 25,000 | Planned | 20 | Medium
TSK-004 | Development Phase - Backend | 2024-04-11 | 2024-06-30 | 90 | Software Engineer Head | 75,000 | Scheduled | 10 | High
TSK-005 | User Testing & Feedback Loop | 2024-07-01 | 2024-07-31 | 31 | QA Manager | 18,000 | Not Started | 0 | High