## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
TSK-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | 1
TSK-002 | Requirement Gathering | John Smith | 2024-04-02 | 2024-04-10
TSK-003 | Design Phase Finalization | Sarah Lee | 2024-04-11 | 2024-04-18
TSK-004 | Development Sprint 1 | Mike Brown | 2024-04-19 | 2024-05-03
TSK-005 | Testing & Bug Fixing | Lisa Wong | 2024-05-04 | 2024-05-17
TSK-006 | Final Review & Approval | Team Lead | 2024-05-18 | 2024-05-18
TSK-007 | Go-Live Deployment | DevOps Team | 2024-05-19 | 2024-05-19