## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | High | Completed | Initial planning session with stakeholders.
T002 | Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | High | In Progress | Collect input from department heads.
T003 | Design Phase | Mike Johnson | 2024-04-11 | 2024-04-25 | Medium | Not Started | Create wireframes and UI mockups.
T004 | Development Phase | Sarah Lee | 2024-04-26 | 2024-05-15 | High | Not Started | Implement backend and frontend code.
T005 | Testing & Quality Assurance | David Brown | 2024-05-16 | 2024-05-30 | High | Not Started | Run unit and integration tests.