## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation
TSK-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-03 | 3 | High | In Progress | None | Project Manager, Marketing Lead
TSK-002 | Market Research Analysis | Mark Smith | 2024-04-04 | 2024-04-15 | 12 | Medium | Planned | TSK-001 | Research Team, Data Analyst
TSK-003 | Prototype Development | Alex Chen | 2024-04-16 | 2024-05-10 | 25 | High | Not Started | TSK-002 | Engineering Team, UX Designer
TSK-004 | User Testing Phase | Sarah Lee | 2024-05-11 | 2024-05-30 | 19 | Medium | Not Started | TSK-003 | QA Team, Product Owner
TSK-005 | Final Product Review | David Kim | 2024-06-01 | 2024-06-05 | 5 | High | Not Started | TSK-004 | Stakeholders, Leadership Team