## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Progress (%)
T-001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | 1 | High | Completed | None | 100%
T-002 | Requirements Gathering | John Smith | 2024-03-16 | 2024-04-05 | 19 | Medium | In Progress | T-001 | 65%
T-003 | Design Phase Finalization | Sarah Lee | 2024-04-06 | 2024-04-20 | 15 | High | Planned | T-002 | 0%
T-004 | Development Sprint 1 | Mike Johnson | 2024-04-21 | 2024-05-10 | 20 | High | Scheduled | T-003 | 0%
T-005 | Testing & QA Review | Lisa Chen | 2024-05-11 | 2024-05-31 | 21 | Medium | Scheduled | T-004 | 0%