## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
T001 | Project Kickoff Meeting | John Smith | 2023-10-01 | 2023-10-01 | 1 | High | Completed
T002 | Market Research Survey | Sarah Lee | 2023-10-03 | 2023-10-15 | 13 | Medium | In Progress | T001
T003 | Design Wireframes | Mike Chen | 2023-10-16 | 2023-10-25 | 10 | High | Planned | T002
T004 | Development Phase Start | Lisa Wong | 2023-10-26 | 2023-11-15 | 20 | High | Pending | T003
T005 | Testing & QA Review | David Park | 2023-11-16 | 2023-11-30 | 15 | Medium | Planned | T004
T006 | Final Review & Launch | Team Lead | 2023-12-01 | 2023-12-05 | 5 | High | Pending | T005