## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
T001 | Project Initiation Meeting | John Doe | 2024-03-15 | 2024-03-15 | 1 | High | Completed
T002 | Requirements Gathering | Jane Smith | 2024-03-16 | 2024-03-25 | 10 | High | In Progress | T001
T003 | Design Phase Finalization | Mike Johnson | 2024-03-26 | 2024-04-10 | 15 | Medium | Planned | T002
T004 | Development Sprint 1 | Sarah Lee | 2024-04-11 | 2024-04-25 | 15 | High | Not Started | T003
T005 | Testing and QA Review | David Brown | 2024-04-26 | 2024-05-10 | 15 | High | Planned | T004
T006 | Final Deployment | Emily Clark | 2024-05-11 | 2024-05-15 | 5 | Critical | Not Started | T005