## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 1 | High | Completed | None | Initial project planning session.
T002 | Requirement Gathering | Sarah Lee | 2024-04-02 | 2024-04-15 | 14 | High | In Progress | T001 | Collect user needs and define scope.
T003 | Design Phase | Michael Chen | 2024-04-16 | 2024-05-10 | 25 | Medium | Not Started | T002 | Wireframes and UI mockups.
T004 | Development Phase | Linda Patel | 2024-05-11 | 2024-07-31 | 82 | High | Not Started | T003 | Implement core features.
T005 | Testing & QA | David Kim | 2024-08-01 | 2024-08-15 | 15 | High | Not Started | T004 | Functional and usability testing.
T006 | Deployment & Go-Live | Emma Wilson | 2024-08-16 | 2024-08-16 | 1 | High | Not Started | T005 | Launch the solution to production.