## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 0 | High | Completed | None | Finalize project vision and team assignments.
T002 | Market Research | Sarah Lee | 2024-04-02 | 2024-04-15 | 14 | Medium | In Progress | T001 | Gather user insights and competitor analysis.
T003 | UI/UX Design Phase | Mike Chen | 2024-04-16 | 2024-05-05 | 20 | High | Planned | T002 | Create wireframes and user flow diagrams.
T004 | Development Sprint | Linda Wong | 2024-05-06 | 2024-06-15 | 40 | Critical | Not Started | T003 | Build core application modules with testing integration.
T005 | User Testing & Feedback | David Kim | 2024-06-16 | 2024-06-30 | 15 | High | Scheduled | T004 | Collect real user feedback on usability and functionality.