## Worksheet
Project Name | Task ID | Task Description | Owner | Start Date | End Date | Status | Priority | Quarterly Phase | Dependencies
Q4 Marketing Campaign | TASK-001 | Develop brand messaging and visuals for Q4 launch. | Sarah Thompson | 2023-10-01 | 2023-10-31 | In Progress | High | Q4 Initiation | Design approval from Q3 team
Product Development Phase 2 | TASK-002 | Finalize user interface and conduct usability testing. | James Wilson | 2023-11-15 | 2023-12-15 | Planned | High | Q4 Execution | Completion of Phase 1 deliverables
Customer Onboarding Program | TASK-003 | Launch new onboarding workflow and training modules. | Linda Chen | 2023-11-01 | 2023-12-31 | Not Started | Medium | Q4 Growth | Access to CRM system update
Q4 Financial Review | TASK-004 | Analyze Q3 performance and prepare forecast for Q4. | David Park | 2023-10-15 | 2023-11-30 | Completed | Medium | Q4 Planning | None