## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (days) | Priority | Status | Dependencies
T001 | Project Planning | John Doe | 2024-03-15 | 2024-03-18 | 4 | High | Completed | None
T002 | Requirement Analysis | Jane Smith | 2024-03-19 | 2024-03-25 | 7 | High | In Progress | T001
T003 | UI/UX Design | Alex Chen | 2024-03-26 | 2024-04-05 | 10 | Medium | Pending | T002
T004 | Development Phase | Mike Turner | 2024-04-06 | 2024-05-10 | 35 | High | Not Started | T003
T005 | Testing & QA | Sarah Kim | 2024-05-11 | 2024-05-25 | 15 | High | Not Started | T004