## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%)
T001 | Project Initiation | Jane Smith | 2024-03-15 | 2024-03-20 | 5 | Completed | High | - | 100%
T002 | Requirements Gathering | Michael Johnson | 2024-03-21 | 2024-04-10 | 30 | In Progress | High | T001 | 65%
T003 | Design Phase | Sophia Lee | 2024-04-11 | 2024-05-15 | 35 | Planned | Medium | T002 | 0%
T004 | Development | David Kim | 2024-05-16 | 2024-07-31 | 75 | HighPending | 90%
T005 | Testing & QA | Lena Brown | 2024-08-01 | 2024-08-31 | 31 | Not Started | High | T004 | 0%