## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | Team Lead | 2024-03-15 | 2024-03-15 | 1 | High | Completed |  | All team members to attend and finalize project scope.
T002 | Requirements Gathering | Product Owner | 2024-03-16 | 2024-03-25 | 7 | High | In Progress | T001 | Collect input from stakeholders and document functional requirements.
T003 | Design Phase - Wireframes | UI/UX Designer | 2024-03-26 | 2024-04-05 | 10 | Medium | Not Started | T002 | Create initial wireframes based on requirements.
T004 | Development Start | Full Stack Team | 2024-04-06 | 2024-05-15 | 40 | High | Not Started | T003 | Begin coding with approved design and API documentation.
T005 | Testing & QA Phase | QA Engineer | 2024-05-16 | 2024-05-31 | 15 | High | Not Started | T004 | Conduct unit, integration, and user acceptance testing.
T006 | Deployment & Go-Live | DevOps Engineer | 2024-06-01 | 2024-06-03 | 3 | High | Not Started | T005 | Deploy application to production environment.