## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
T-001 | Project Initiation | John Doe | 2024-04-01 | 2024-04-05 | 5 | High | Planned
T-002 | Requirements Gathering | Jane Smith | 2024-04-06 | 2024-04-15 | 10 | High | In Progress | T-001
T-003 | Design Phase | Alex Johnson | 2024-04-16 | 2024-04-30 | 15 | Medium | Planned | T-002
T-004 | Development Phase | Sarah Lee | 2024-05-01 | 2024-06-15 | 56 | High | Not Started | T-003
T-005 | Testing & QA | Mike Chen | 2024-06-16 | 2024-07-10 | 35 | High | Planned | T-004
T-006 | Deployment & Go-Live | Lisa Wong | 2024-07-11 | 2024-07-15 | 5 | Medium | Not Started | T-005
Total Tasks: 6