## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%) | Dependencies | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-03 | Completed | High | 100% |  | Finalize project scope and team assignments.
T002 | Requirements Gathering | Sarah Lee | 2024-04-04 | 2024-04-15 | In Progress | High | 65% | T001 | Collect user needs and validate with stakeholders.
T003 | Design Phase | Michael Chen | 2024-04-16 | 2024-05-10 | Planned | Medium | 0% | T002 | Develop wireframes and UI mockups.
T004 | Development Start | Lena Torres | 2024-05-11 | 2024-07-31 | Not Started | Medium | 0% | T003 | Begin coding based on approved designs.
T005 | Testing & QA | David Kim | 2024-08-01 | 2024-08-31 | Scheduled | High | 0% | T004 | Conduct functional and performance testing.