## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resources Required
T001 | Project Initiation & Planning | John Smith | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | None | Project Manager, Stakeholders
T002 | Requirements Gathering Workshop | Sarah Lee | 2024-03-16 | 2024-03-25 | 10 | High | Not Started | T001 | Business Analysts, Clients
T003 | Design Phase - UI/UX Prototyping | Mike Johnson | 2024-03-26 | 2024-04-10 | 15 | Medium | Planned | T002 | UI/UX Designer, Product Owner
T004 | Development Sprint 1 | Emily Davis | 2024-04-11 | 2024-05-15 | 35 | High | Not Started | T003 | Software Developers, QA Team
T005 | Testing & Quality Assurance | David Wong | 2024-05-16 | 2024-06-10 | 35 | High | Planned | T004 | QA Engineers, DevOps
T006 | Deployment & Go-Live | Lisa Chen | 2024-06-11 | 2024-06-15 | 5 | Critical | Not Started | T005 | DevOps, IT Operations