## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status | Dependencies
T001 | Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | J. Smith | High | Completed | None
T002 | <1 td>Requirements Gathering2024-03-02 | 2024-03-15 | 14 | A. Johnson | High | In Progress | T001
T003 | Design Phase | 2024-03-16 | 2024-04-10 | 35 | M. Davis | Medium | Not Started | T002
T004 | Development Phase | 2024-04-11 | 2024-06-30 | 81 | L. Brown | High | Not Started | T003
T005 | Testing & QA | 2024-07-01 | 2024-07-31 | 31 | K. Wilson | High | Not Started | T004
T006 | Deployment & Go-Live | 2024-08-01 | 2024-08-05 | 5 | R. Taylor | High | Not Started | T005