## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Business Analyst | In Progress
Design Phase | 2024-04-11 | 2024-04-25 | 15 | UX Designer | Not Started
Development Phase | 2024-04-26 | 2024-05-31 | 36 | Development Team | Not Started
Testing Phase | 2024-06-01 | 2024-06-15 | 15 | QA Team | Not Started
Deployment | 2024-06-16 | 2024-06-16 | 1 | IT Operations | Not Started
Post-Deployment Review | 2024-06-17 | 2024-06-17 | 1 | Project Manager | Not Started