## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies
T-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | Completed | High | None
T-002 | Requirements GatheringSarah Kim | 2024-04-02 | 2024-04-15 | 14 | In Progress | High | T-001
T-003 | Design Phase Final Review | Michael Lee | 2024-04-16 | 2024-04-25 | 10 | Not Started | Medium | T-002
T-004 | Development Phase Begin | Lisa Wong | 2024-04-26 | 2024-05-31 | 36 | Not Started | High | T-003
T-005 | Testing & Quality Assurance | David Park | 2024-06-01 | 2024-06-15 | 15 | Not Started | High | T-004
T-006 | Final Review & Deployment | Emily Chen | 2024-06-16 | 2024-06-20 | 5 | Not Started | Critical | T-005