## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Responsible Party | Status | Priority
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed | High
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Business Analysts | In Progress | High
Design Phase | 2024-04-11 | 2024-05-15 | 35 | UI/UX Team | Pending | Medium
Development Phase | 2024-05-16 | 2024-07-31 | 76 | Development Team | Planned | High
Testing & QA | 2024-08-01 | 2024-08-31 | 31 | QA Engineers | Scheduled | High
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | DevOps Team | Pending | Critical
Post-Launch Support | 2024-09-16 | 2024-10-31 | 46 | Support Team | Planned | Medium