## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%)
T-001 | Project Kickoff Meeting | John Doe | 2024-03-15 | 2024-03-15 | 1 | Completed | Low | None | 100%
T-002 | Requirements Gathering | Jane Smith | 2024-03-16 | 2024-03-25 | 10 | In Progress | Medium | T-001 | 65%
T-003 | UI/UX Design | Alex Johnson | 2024-03-26 | 2024-04-10 | 15 | Planned | High | T-002 | 0%
T-004 | Development Phase | Team A | 2024-04-11 | 2024-05-31 | 60 | Not Started | High | T-003 | 0%
T-005 | Testing & Quality Assurance | QA Team | 2024-06-01 | 2024-06-15 | 15 | Not Started | Medium | T-004 | 0%
T-006 | Deployment & Launch | DevOps Team | 2024-06-16 | 2024-06-18 | 3 | Not Started | Low | T-005 | 0%