## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority | Dependencies
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Jane Smith | Completed | High | None
T002 | <Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | John Doe | In Progress | High | T001
T003 | Design Phase Finalization | 2024-03-26 | 2024-04-05 | 10 | Lisa Chen | Not Started | Medium | T002
T004 | Development Phase Start | 2024-04-06 | 2024-05-15 | 41 | Mike Turner | Not Started | High | T003
T005 | Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 | Sarah Lee | <Not Started | High | T004
T006 | Deployment & Go-Live | 2024-06-11 | 2024-06-15 | 5 | David Kim | Not Started | High | T005