## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%) | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-03-01 | 2024-03-01 | 1 | Completed | High |  | 100 | Finalized project scope and objectives.
T002 | Requirements Gathering | Jane Smith | 2024-03-02 | 2024-03-15 | 14 | In Progress | High | T001 | 65 | Collecting input from stakeholders.
T003 | Design Phase | Mike Johnson | 2024-03-16 | 2024-04-10 | 35 | Planned | Medium | T002 | 0 | UI/UX wireframes to be finalized.
T004 | Development Phase (Phase 1) | Sarah Lee | 2024-04-11 | 2024-05-30 | 60 | Scheduled | High | T003 | 0 | Build core functionality modules.
T005 | Testing & Quality Assurance | David Kim | 2024-06-01 | 2024-06-30 | 30 | Planned | High | T004 | 0 | Execute functional and regression tests.
T006 | Deployment & Go-Live | Lisa Wong | 2024-07-01 | 2024-07-05 | 5 | Scheduled | Critical | T005 | 0 | Final deployment to production environment.
T007 | Post-Deployment Review | John Doe | 2024-07-06 | 2024-07-10 | 5 | Planned | Medium |  | 0 | Assess performance and gather feedback.