## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (days) | Status | Dependencies | Priority | Progress (%)
T001 | Project Kickoff Meeting | Jane Doe | 2024-03-01 | 2024-03-01 | 1 | Completed | None | High | 100
T002 | Requirements Gathering | John Smith | 2024-03-02 | 2024-03-15 | 14 | In Progress | T001 | High | 60
T003 | Design Phase | Sarah Lee | 2024-03-16 | 2024-04-10 | 35 | Not Started | T002 | Medium | 0
T004 | Development Phase | Mike Brown | 2024-04-11 | 2024-06-30 | 81 | Not Started | T003 | High | 0
T005 | Testing & QA | Lisa Chen | 2024-07-01 | 2024-07-31 | 31 | Not Started | T004 | High | 0
T006 | Final Review & Deployment | Admin Team | 2024-08-01 | 2024-08-15 | 15 | Not Started | T005 | High | 0