## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%)
T-001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | High | 100
T-002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | In Progress | High | 75
T-003 | Design Phase Review | Mike Chen | 2024-03-26 | 2024-04-05 | Pending | Medium | 0
T-004 | Development Start | Lisa Park | 2024-04-06 | 2024-05-15 | Not Started | Medium | 0
T-005 | Testing & Quality Assurance | David Wong | 2024-05-16 | 2024-06-10 | Planned | High | 0