## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status | Dependencies | Milestones | Progress (%)
T-001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Project Manager | High | Completed | - | Kickoff | 100
T-002 | Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | Business Analyst | High | In Progress | T-001 | - | 60
T-003 | Design Phase Finalization | 2024-03-26 | 2024-04-10 | 15 | UI/UX Designer | Medium | Not Started | T-002 | Design Review | 0
T-004 | Development Sprint 1 | 2024-04-11 | 2024-04-25 | 15 | Software Engineer Team | High | Not Started | T-003 | - | 0
T-005 | Testing & QA Phase | 2024-04-26 | 2024-05-15 | 20 | QA Lead | High | Not Started | T-004 | Pre-Release Test | 0
T-006 | Deployment to Staging | 2024-05-16 | 2024-05-18 | 3 | DevOps Engineer | Critical | Not Started | T-005 | Staging Launch | 0
T-007 | UAT & Final Sign-off | 2024-05-19 | 2024-05-25 | 7 | Project Sponsor | High | Not Started | T-006 | Go-Live Approval | 0
T-008 | Production Deployment | 2024-05-26 | 2024-05-31 | 6 | DevOps Engineer | Critical | Not Started | T-007 | Production Launch | 0