## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Budget Allocation ($) | Responsible Team | Status | Progress (%) | Milestone Flag
TSK-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | 50,000 | Project Management Team | Completed | 100% | ✓
TSK-002 | <Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 | 75,000 | Strategy & Analytics Team | On Track | 85% | •
TSK-003 | Product Design & Prototyping | 2024-04-11 | 2024-05-31 | 61 | 150,000 | Design & Engineering Team | In Progress | 60% | •
TSK-004 | Development & Testing Phase | 2024-06-01 | 2024-08-31 | 90 | 350,000 | Engineering & QA Team | Not Started | 0% | –
TSK-005 | Launch & Marketing Campaign | 2024-09-01 | 2024-10-31 | 60 | 180,000 | Marketing Team | Planned | 0% | –