## Worksheet
Task | Start Date | End Date | Duration (days) | Assigned To | Priority | Status
Project Kickoff Meeting | 2023-10-01 | 2023-10-01 | 1 | Freelancer A | High | Completed
Requirements Gathering | 2023-10-02 | 2023-10-08 | 7 | Freelancer B | High | In Progress
Design Phase (Wireframes) | 2023-10-09 | 2023-10-15 | 7 | Freelancer C | Medium | Pending
Development Phase (Frontend) | 2023-10-16 | 2023-10-30 | 15 | Freelancer D | High | Not Started
Testing & Bug Fixing | 2023-11-01 | 2023-11-07 | 7 | Freelancer E | High | Planned
Final Review & Sign-off | 2023-11-08 | 2023-11-08 | 1 | Project Manager | High | Not Started