## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%)
TSK-001 | Project Kickoff Meeting | John Smith | 2024-03-01 | 2024-03-01 | 1 | Completed | High | None | 100%
TSK-002 | Requirements Gathering | Sarah Lee | 2024-03-02 | 2024-03-15 | 14 | In Progress | High | TSK-001 | 65%
TSK-003 | UI/UX Design Finalization | Mike Johnson | 2024-03-16 | 2024-03-30 | 15 | Not Started | Medium | TSK-002 | 0%
TSK-004 | Frontend Development | Alex Chen | 2024-04-01 | 2024-04-30 | 30 | Not Started | High | TSK-003 | 0%
TSK-005 | Backend Integration | Emma Rodriguez | 2024-05-01 | 2024-05-31 | 31 | Not Started | High | TSK-004 | 0%
TSK-006 | Testing & Quality Assurance | David Kim | 2024-06-01 | 2024-06-30 | 30 | Not Started | Medium | TSK-005 | 0%
TSK-007 | User Training & Go-Live | Linda Wilson | 2024-07-01 | 2024-07-31 | 31 | Not Started | Low | TSK-006 | 0%