## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority | Dependencies
TSK-001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | John Smith | Completed | High
TSK-002 | Requirements Gathering2024-03-16 | 2024-03-25 | 10 | Lisa Chen | In Progress | High | TSK-001
TSK-003 | Design Phase Final Review | 2024-03-26 | 2024-04-01 | 6 | Mike Rodriguez | Pending | Medium | TSK-002
TSK-004 | Development Phase Start | 2024-04-02 | 2024-05-15 | 55 | Sarah Kim | Planned | High | TSK-003
TSK-005 | Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 | David Lee | Scheduled | High | TSK-004
TSK-006 | Deployment & Go-Live | 2024-06-11 | 2024-06-15 | 5 | Rachel Park | Not Started | Critical | TSK-005