## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies
TSK-001 | Project Initiation & Planning | John Smith | 2024-03-01 | 2024-03-15 | 15 | High | Planned
TSK-002 | Market Research & Analysis | Sarah Lee | 2024-03-16 | 2024-03-31 | 16 | Medium | In Progress | TSK-001
TSK-003 | Design Phase & Prototyping | Mike Chen | 2024-04-01 | 2024-04-30 | 30 | High | Scheduled | TSK-002
TSK-004 | Development & Coding | Anna Park | 2024-05-01 | 2024-06-15 | 65 | High | Not Started | TSK-003
TSK-005 | Testing & Quality Assurance | David Kim | 2024-06-16 | 2024-07-10 | 35 | High | Planned | TSK-004
TSK-006 | Deployment & Launch | Lena Garcia | 2024-07-11 | 2024-07-15 | 5 | Medium | Scheduled | TSK-005
Total Tasks: | [7 empty] | 6