## Worksheet
Task ID | Task Name | Start Date | End Date | Assigned To | Status | Priority | Dependencies
T101 | Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | John Smith | Completed | High
T102 | Requirements Gathering | 2024-03-02 | 2024-03-15 | Jane Doe | In Progress | High | T101
T103 | Design Phase Completion | 2024-03-16 | 2024-03-31 | Mike Johnson | Not Started | Medium | T102
T104 | Development Begin | 2024-04-01 | 2024-05-15 | Sarah Lee | Planned | High | T103
T105 | Testing Phase | 2024-05-16 | 2024-06-10 | David Brown | Not Started | High | T104